## README
SUNOI — Task Tracker
Why this is ONE tab, not separate Marketing/Ops/Todo tabs
The instinct is to split into a Marketing tab, an Ops tab, a Todo tab — it feels organized, but with only
2 people it backfires: you have to remember to check 3 places, and whichever tab isn't open in front of
you goes stale first. One flat list with a Category column does the same job and can't be forgotten.
How to use it:
1. Everything goes in the 'All Tasks' tab — marketing, ops, menu, legal, accounting, launch. One list.
2. Use the Category, Owner, Priority, and Status columns (dropdowns) to filter/sort instead of splitting tabs.
3. In Google Sheets: Data > Create a filter view to make your own personal view (e.g. 'James, not done')
WITHOUT disrupting the shared sort order others see. Don't just use the basic filter — it changes the
view for everyone editing at once.
4. Check the 'Dashboard' tab for a live auto-updating count by status/category — no manual counting.
5. Once a month (or whenever the list feels cluttered), filter Status = Done and move those rows to the
'Archive' tab (cut/paste). Don't delete history, just get it out of your daily view.
6. Add new rows as things come up — don't wait for a 'planning session' to update it. If it's not in the
sheet, it doesn't exist as far as tracking goes.
Seeded with the current real backlog (as of 2026-07-25) from the sunoi/ project docs — not empty, so it's
usable immediately. Update statuses as you actually do the work.

## Dashboard
SUNOI — Task Dashboard
Auto-updates from 'All Tasks' — no manual counting.
By Status |  | By Category
Status | Count | Category | Open (not Done)
Not Started |  | Menu R&D
In Progress |  | Marketing
Blocked |  | Operations
Done |  | Legal/Platform
Accounting
Launch
By Owner (open tasks) |  | High Priority, Not Done
Owner | Open Tasks | Count
James
Hien
Both

## All Tasks
ID | Task | Category | Owner | Priority | Status | Due Date | Source/Linked Doc | Notes
1 | Recipe/taste testing for all 10+ drinks | Menu R&D | Hien | High | In Progress | 2026-07-28 | 02-full-backlog-to-launch.md | Current pacing bottleneck for launch
2 | Lock final recipe specs (ratios, sweetness/ice levels, toppings) | Menu R&D | Hien | High | Not Started | 2026-07-29 | 02-full-backlog-to-launch.md
3 | Cost each drink (ingredient cost per unit) | Menu R&D | Hien | High | Not Started | 2026-07-30 | 02-full-backlog-to-launch.md | Feeds pricing/margin sheet
4 | Finalize sizes offered and price per size | Menu R&D | Hien | High | Not Started | 2026-07-29 | 02-full-backlog-to-launch.md
5 | Decide topping/customization options and upcharges | Menu R&D | Hien | Medium | Not Started | 2026-07-29 | 02-full-backlog-to-launch.md
6 | Write internal recipe/spec sheet for SOP | Menu R&D | Hien | Medium | Not Started | 2026-07-29 | 02-order-to-delivery-sop.md | So a future 3rd person could follow it
7 | Outside taste-test feedback (not just the 2 of you) | Menu R&D | Both | Medium | Not Started | 2026-07-28 | 02-full-backlog-to-launch.md
8 | Shelf-life/quality check per drink | Menu R&D | Hien | Low | Not Started | 2026-07-30 | 02-full-backlog-to-launch.md | Matters for delivery time tolerance
9 | Verify competitor pricing directly on live GrabFood/ShopeeFood | Marketing | James | High | Not Started | 2026-07-28 | 00-launch-plan.md | Google Maps data isn't real pricing
10 | Target customer research (who's actually in the 2-3km radius) | Marketing | James | Medium | Not Started | 2026-07-27 | 00-launch-plan.md
11 | Positioning/differentiation strategy vs. real competitors | Marketing | James | Medium | Not Started | 2026-07-28 | 00-launch-plan.md
12 | Fill in real content calendar through launch | Marketing | James | Medium | Not Started | 2026-07-29 | 00-launch-plan.md
13 | Identify 2-3 specific local FB groups to post in | Marketing | James | Medium | Not Started | 2026-07-30 | 00-launch-plan.md
14 | Set up Zalo OA/group for direct orders | Marketing | James | High | Not Started | 2026-07-31 | 00-launch-plan.md
15 | Write platform listing copy (item names/descriptions) | Marketing | James | Medium | Not Started | 2026-07-30 | 00-launch-plan.md
16 | Write brand bio (VN + EN) | Marketing | Hien | Low | Not Started | 2026-07-31 | 00-launch-plan.md
17 | Apply to GrabFood + ShopeeFood new-merchant promo programs | Marketing | James | High | Not Started | 2026-07-30 | 00-launch-plan.md | Terms need direct confirmation from platform support
18 | Schedule sampling day at KDC Song Da (week 3) | Marketing | Both | Low | Not Started | 2026-08-10 | 00-launch-plan.md | ~500-800k VND per 100 cups
19 | Reach out to 1-2 nano/micro-influencers | Marketing | James | Low | Not Started | 2026-08-05 | 00-launch-plan.md | 200k-1M VND per post + free product
20 | Confirm packaging is waterproof/leak-proof (rainy season) | Marketing | Hien | Medium | Not Started | 2026-07-31 | 00-launch-plan.md | Ties to ops packaging stress-test
21 | Assign informal shift roles for week 1 | Operations | Both | Medium | Not Started | 2026-07-27 | 02-full-backlog-to-launch.md
22 | Dry-run the full SOP end-to-end with real menu | Operations | Both | High | Not Started | 2026-08-01 | 02-order-to-delivery-sop.md
23 | Set 20-30 drinks/day cap on both platforms | Operations | James | Medium | Not Started | 2026-08-02 | 02-full-backlog-to-launch.md
24 | Identify backup ingredient supplier | Operations | Hien | Medium | Not Started | 2026-07-28 | 05-inventory-cost-tracker.xlsx | Primary supplier already confirmed
25 | Decide rest/backup coverage plan (7-day/8am-9pm schedule) | Operations | Both | Medium | Not Started | 2026-08-05 | 02-full-backlog-to-launch.md | Still genuinely unresolved
26 | Packaging stress-test (leak-proof, transit-safe) | Operations | Hien | Medium | Not Started | 2026-07-31 | 02-full-backlog-to-launch.md
27 | Gather ID + bank account proof for platform applications | Legal/Platform | James | High | Not Started | 2026-07-27 | 00-test-phase-roadmap.md | ID-only path, staying informal
28 | Submit GrabFood merchant application | Legal/Platform | James | High | Not Started | 2026-07-30 | 01-week-2026-07-27-action-plan.md
29 | Submit ShopeeFood merchant application | Legal/Platform | James | High | Not Started | 2026-07-30 | 01-week-2026-07-27-action-plan.md
30 | Decide on Baemin (launch scope or later) | Legal/Platform | James | Low | Not Started | 2026-08-02 | 00-test-phase-roadmap.md
31 | Confirm Zalo payment methods work (cash/bank/Momo/ZaloPay) | Legal/Platform | James | Medium | Not Started | 2026-07-31 | 01-week-2026-07-27-action-plan.md
32 | Fill pricing/margin sheet with real per-drink numbers | Accounting | Hien | High | Not Started | 2026-07-31 | 02-pricing-margin-check.csv
33 | Confirm no drink loses money on platform orders after commission | Accounting | Hien | High | Not Started | 2026-07-31 | 02-pricing-margin-check.csv
34 | Build daily habit of logging orders/expenses | Accounting | Both | Medium | Not Started | 2026-08-02 | 01-order-log.csv | Trackers exist, need to become routine
35 | Confirm/adjust proposed success criteria for the test phase | Accounting | Both | Low | Not Started | 2026-08-05 | 00-test-phase-roadmap.md | AI-proposed bar still pending sign-off
36 | Soft launch to friends & family (direct Zalo only) | Launch | Both | High | Not Started | 2026-08-02 | 01-week-2026-07-27-action-plan.md | Flexible date, depends on menu lock
37 | Soft-launch retro | Launch | Both | Medium | Not Started | 2026-08-03 | 01-week-2026-07-27-action-plan.md
38 | Go live on GrabFood/ShopeeFood listings | Launch | James | High | Not Started | 2026-08-03 | 01-week-2026-07-27-action-plan.md
39 | Public marketing push (FB groups + wider Zalo broadcast) | Launch | Both | Medium | Not Started | 2026-08-04 | 00-launch-plan.md

## Archive
SUNOI — Archived (Done) Tasks
Cut/paste completed rows here from 'All Tasks' periodically (e.g. monthly) to keep the main list lean. Same columns as All Tasks.
ID | Task | Category | Owner | Priority | Status | Due Date | Source/Linked Doc | Notes